## Sheet1
Priority Area | Date of Committee Meeting | Blueprint Function | Executive Lead | Non Executive Lead | Operational Lead | Objective | Specific Actions | Timeline | Status | Intended Good Governance Outcome | Status Update One | Status Update Two
Performance | FRP - 3 November | Holding to Account, Assurance Framework | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | Performance reporting to triangulate with other NHS Highland data, including patient experience, and use trajectories, trends and benchmarking with other Boards & systems, | Data in IPQR to include wider in-house data to assist with triangulation and to refer to any live critical issues facing NHS Highland. IPQR also to include description of trends, trajectories and benchmark with other Boards. | 2023-12-31 | Complete | Better understanding of whole system performance, improved scrutiny of data and enhanced holding to account of Executives. Improvement to assurance at Board level and create opportunity for 'deep dives' where necessary. Provide opportunity to triangulate data with external reports and benchmarking information. Better oversight and consistency of system-wide assurance at Board level. Greater clarity of expectation and understanding where progress is not being made. | Lorraine Cowie 21/12/23 - All data now has national benchmarking and a clearer description of progress made and work still to complete with timescales. All areas have trajectories where agreed and once integrated service planning is complete this will improve further. Benchmarking is available on all pages of IPR.
| FRP - 3 November |  | Deputy Chief Executive | Chair FRP Committee | Head of Strategy & Transformation Directorates and operational units | IPQR to make explicit linkage with quality of care and outcomes. | Incorporate patient experience into IPQR with explicit reference to care and outcomes. | 2024-07-31 | progressing | Better responsiveness to the rights and interests of patients and stakeholders in the healthcare system. Development of trust and increase public confidence in the organisation as a public body. | Lorraine Cowie 21/12/2023 Head of Strategy and Transformation has agreed a test of change to be used for the March FRP Committee IPQR relating to cancer and radiology where care opinion and QPIs are embedded. This pilot will be reviewed to expand to other areas once the test of change has been approved.
Finance & Best Value | FRP - 3 November | Setting Direction, Assurance Framework | Director of Finance, Deputy Chief Executive | Chair FRP Committee |  | Creation of a framework for business change/service redesign to evidence the value of expenditure with links to ADP & finance. | Review proforma for approval of business cases, evolve a checklist to ensure good decisions and best value for the wider organisation. Best Value to be based on Realistic Medicine definition. | 2023-12-31 | progressing | Improved and better evidenced and assured decisions on investment/disinvestment in delivery of services. Improvements in forward planning, horizon scanning and awareness of associated risks. Improvements in connection and professional advice from ACF and APF. Better contribution from ACF and APF in terms of shaping policy and strengthening their voice at the Board. | Heledd Cooper 09/10/2023 Still a work in progress and the intention is to align the financial planning, performance and workforce planning for 24/25 budget setting. Heledd is working on a document to set this out. Lorraine Cowie 21/12/23 New Integrated Service Planning and the ADP guidance has set this out and will create a baseline for redesign. Realistic medicine has a clear project plan and is part of the strategy & transformation team. 15 box model produced by SG has a clear improvement plan developed and approved by EDG.
| FRP - 5 January |  | Director of Finance and | ACF and APF stakeholder members | Board Secretary | Advisory Boards to inform and be part of the decision making process for business change. | Hold a development session and engage with APF and ACF to initiate improvements in co-production, engagement and involvement with business change processes and governance. | 2023-12-31 | Complete | Board members gain a fuller picture of the issues, risks and opportunities facing the organisation. Board members thinking and decisions are informed by issues affecting the workforce and benefit from the advice from clinical colleagues on issues that could affect clinical practice and employee relations. Assists the Board in discussions with other key stakeholders. | ACF and APF will hold discussions at their January & February 2024 meetings on ‘Processes for business change – Advisory Board engagement’ covering staffing, Performance, Planning and Finance
Risk | September Board Development Session | Risk, Assurance Framework | Medical Director | Chair Audit Committee |  | Board to reset its Risk Appetite | Board to refine the risk framework and refine the risk appetite statement in consultation with clinicians - to be brought back to a Board Development Session withn 2023-24 | 2023-12-31 | Complete | A more active approach to governance to make more timely, well informed and strategic decisions. Better skills in identifying, escalating and managing issues. Evidence of staff being empowered to manage risk with a clearer understanding of the Board's risk appetite and tolerance being evident at Committee and Board level. Board to get assurance on the same approach to risk being followed throughout the organisation. Clearer focus on horizon scanning being evident through SBARs to Committees and the Board. | Boyd Peters The Board Risk Appetite was agreed by the Board in November 2023. The next phase (using the risk appetite within the strategic and operational parts of NHS Highland) will occur throughout 2024.
| 2023-02-06 |  | Medical Director | Chair Audit Committee |  | Translation of revised risk appetite into workable processes for colleagues | Review and revise organisational controls in line with revised risk appetite. | 2024-07-31 | progressing | Improved alignment of organisation's operations with the wider strategic and policy context. | Boyd Peters 28/09/2023 - Will occur during 2024
| 2023-02-06 |  | Medical Director | Chair Audit Committee |  | Upskilling workforce in risk management knowledge and methodology | Devise and cascade organisational training to support and empower colleagues to take appropriate decisions flowing from the revised risk appetite. | 2024-07-31 | progressing | Colleagues are better informed to rapidly identify, escalate and manage issues which might otherwise not have been identified. | Boyd Peters 28/09/2023 Will occur during 2024
| COMPLETED |  | Director of Finance | Chair Audit Committee | Board Secretary | Audit Committee to include oversight of the risk process within its ToR | This is already in place. | 2023-12-31 | Complete |  | Complete
Culture | Staff Governance 8 November | Influencing Culture | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Clear thread of organisational culture/ethos between front line teams and the Board. Ensure a broader systemic overview of the organisation's ethos incorporating quality, safety and practitioner outcomes with links to the performance framework. Clarity of how this is reflected in the work of governance committees with distinct reference within SBARs. | Fulfilment of the intentions of the ADP for People and Culture. | 2023-12-31 | progressing | Improved alignment of organisation's operations with the wider strategic and policy context. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard | Gareth Adkins 05/10/2023 A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. The medical and nurse director are progressing discussions with stakeholders in relation to the externally commissioned review of our approach to quality. This will develop consensus on next steps for evolving our approach to quality.
| Staff Governance 8 November |  | Chief Executive and Executive Team | Employee Director and Chair Staff Governance Committee | Directorates & senior managers, Head of OD | Reframe and transition of the organisational culture/ethos with emphasis on learning and development throughout the performance framework. | Paper to Staff Governance Committee in September 2023 and initiation of the following: • Focus on developing confidence and capability of management colleagues through a review of the leadership and management programmes • Head of OD to draft a localised proposal on an established nationwide approach to assist colleagues to address staffing matters outwith formal processes and build a proposal over next 3-5 years • Training in compassionate leadership and embrace ‘Civility’ work undertaken by Helen Freeman, with colleague engagement and input • Reestablishment and refresh of Partnership working to maximise the reach of the Area Partnership Forum in terms of employee engagement • Revision of People Processes • Culture Oversight Group to be re-instated | 2023-12-31 | progressing, and some elements completed | Values being shared throughout the organisation about how things are done, how decisions are made, how people interact and work is carried out. Board actively involved in determining, demonstrating and promoting shared values and ethos. Organisation's values being evident at Board and Committee level through SBARs and delivery of Staff Governance Standard | Gareth Adkins 05/10/2023 Cultural oversight group terms of reference reviewed and group re-established and refreshed. A refreshed leadership and culture framework has been discussed with the Cultural oversight group including proposals to strengthen our approach to leadership development and a learning system to support wider engagement with our staff and our leaders in practising compassionate care. This has also progressed through the area partnership forum, staff governance committee and an update provided to the board. A programme of improvement has been established focussed on key people processes starting with recruitment. Further workstreams to be added on payroll and job evaluation Significant work already undertaken to enhance awareness and understanding of partnership working.
| Staff Governance 8 November |  | Director of People and Culture | Employee Director and Chair Staff Governance Committee | Head of Comms and Engagement | Ensure engagement and communication with staff fits within the governance structure | Clarify where staff engagement sits within People and Culture. Clarify permanent ongoing resource and expectations. Establish appropriate process for reporting. Compliance with Staff Governance Standard through Staff Governance Committee and in collaboration with Area Partnership Forum on a yearly basis. | 2023-12-31 | progressing | Improvements in respecting and pursuing the rights and views of staff. Clarity of communication of the organisation's purpose, aims, values, objectives, priorities and targets. Improvement to upholding the Staff Governance Standards. | Gareth Adkins 05/10/2023 Proposal being developed on staff engagement approach building on work already undertaken to establish new methods such as listening and learning panels.
Quality of Care | CGC 7 March HHSC 6 March | Evaluation and Review | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Establish and agree a plan to implement a Quality Framework arising from recent work undertaken with Amanda Croft. | Establish a clear definition, understanding and organisational prioritisation of quality that is underpinned by patient and colleague experience, and National Guidelines. | 2024-07-31 | progressing | A clear link between quality, patient experience and outcomes being evident throughout the organisation and at Committee/Board level. Establishment of a Quality Framework that embeds culture improvement and quality of workplace experience. Quality outcomes triangulate with care opinion. | Louise Bussell - 15/09/2023 The outcome of the Quality review has been presented and discussed at the Area Clinical Forum, the Area Medical Committee, NMAHP Advisory Group, Psychology Leads group, and the Area Pharmacy Committee as part of the development of a consensus on a Quality Framework. April 2024 Board Briefing session planned to focus exclusively on the quality framework and to include Area Clinical Forum colleagues to explore improvements in the Board and ACF's joint working arrangements.
| CGC 7 March HHSC 6 March |  | Nurse Director Medical Director | Chair Clinical Governance Committee |  | Ensure that patient feedback is consistently collected, effectively shared, responded to and utilised across all areas of the Board. | Ensure systems and processes are developed to improve in the collection, reporting and use of patient experience feedback across the Board | 2024-07-31 | progressing | A consistent mechanism to receive patient feedback, to celebrate good practice, learn and improve patient experience. | Louise Bussell - 15/09/2023 Exploring approaches being utilised internally and externally in order to put forward recommendations for establishing consistent patient feedback.
Board Member development | Board Chairs |  | Director of People and Culture | Board Chair | Board Secretary | Training for members to enhance skills in challenge and scrutiny, particularly relating to how the board works effectively in the strategic areas. | Non Exec training plan to be developed to address training needs identified from Non Executive appraisals and succession plan. A workshop to be held to understand the current skill-sets and skills gap, particularly relating to scrutiny and challenge. Further training to be arranged to meet any skills gaps. | 2023-12-31 | Complete | Board members equipped to ask appropriate questions, constructively challenge and scrutinise data to be evidenced at Committee meetings and captured within minutes. Improvement in Board member understanding of the Strategy's alignment with quality improvement. | Ruth Daly - Discussions held with NHS NES colleagues to deliver bespoke training for Board members using current reports and scenario workshops. A detailed programme for the training is being prepared with a view to it being undertaken at the March 2024 Board Development Session. This session will also include colleagues from NHS England National Team for Intensive Support ‘Making Data Count’. An updated succession plan for Non Executives was created to support the Board appointments in December 2023 and will be supplemented going forward with personal development needs arising from appraisals.
SBAR Development | Board Chairs | Evaluation and Review | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to SBAR contents with clear evidence of assurance being offered to improve the Board's assurance and scrutiny role. | Report writers to record how to lift assurance to substantial within SBAR format. Further training and guidance to report authors. | 2023-12-31 | Complete | Clear and consise SBARs to Board and Committee meetings with well evidenced assurance, risks, mitigations, options appraisals. Active use of the Board's agreed Assurance Matrix at Committee and Boad meetings - assurance levels agreed to refer to the appropriate actions available to Committees and Board | Ruth Daly - Improvements to demonstrating how to lift assurance levels now being made with report writers, and updates to training materials for report writers has taken place. Additional sessions for report writers planned to take place before the end of the financial year.
| Board Chairs |  | Executive Team | Board and Committee Chairs | Board Secretary | Improvements to use of assurance maturity matrix within Committee and Board meetings | Committee Chairs to use the assurance matrix to retain better oversight of business that has less than substantial assurance. Chairs to ensure Committees take an active and deliberate focus on the level of assurance during agenda preparation and during Committee meetings. | 2023-12-31 | Complete | An Active approach to delivering good governance with Board and Committees considering the right things, the right evidence and use the tools to bring about the best response. | Ruth Daly - Committee Chairs have refamiliarised themselves with the use of the assurance matrix
Engagement | CGC 2 November HHSC 1 November | Engaging Stakeholders, Influencing Culture, Evaluation and Review | Director of People & Culture, Medical Director, Chief Officer Community, | Chairs Clinical Governance Committee and Highland Health and Social Care Committee | Head of Comms & Engagement | Embedding patient and community representation and feedback within the performance framework and governance structure | Pilot increased publicity of Care Opinion Pilot in Community services and decision made on whether or not to expand Care Opinion to Community services Report on learnings from pilots to HHSCC and CGC in November as part of Community Engagement reporting and capture Highland HSCP assessment of the Engagement Framework's progress as part of this. Continue Highland 100 panel recruitment - ongoing to end of 2023/24 - and send out first survey by December 2023 | 2023-12-31 | Complete | • Learning from Care Opinion to inform whether this is a suitable mechanism for board-wide service user experience reporting • Baseline of experience/perceptions from Highland 100 panel • Panel in place to provide a sounding board for services | Ruth Fry - 15/09/2023 Pilots going well with measurable increase in stories being received and responded to. New services seeking to join the pilot. On embedding patient and community representation, the Care Opinion pilot is complete, and work is currently taking place on the final report. Management of Care Opinion will revert to the Feedback Team. Work ongoing between Strategy and Transformation and Communications and Engagement teams to embed engagement and feedback into planning and redesign protocols. A report on the engagement framework was considered at both Highland Health and Social Care and Clinical Governance Committees in November. The Highland 100 panel contact details are being collated and the first survey is due to go out in January 2024. Highland 100 panel contact details being collated and first survey drafted.