## Implementation Plan
Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Implementation of a Collaborative Vaccination Service - HHSCP Vaccination Teams and General Practice
Milestone Plan
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Last updated 20/03/25 | 2024-12-02
|  | 8 |  | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10 | [6 empty] | 2025-11-17 | [6 empty] | 2025-11-24 | [6 empty] | 2025-12-01 | [6 empty] | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05 | [6 empty] | 2026-01-12 | [6 empty] | 2026-01-19 | [6 empty] | 2026-01-26 | [6 empty] | 2026-02-02 | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09 | [6 empty] | 2026-11-16 | [6 empty] | 2026-11-23 | [6 empty] | 2026-11-30 | [6 empty] | 2026-12-07 | [6 empty] | 2026-12-14 | [6 empty] | 2026-12-21 | [6 empty] | 2026-12-28 | [6 empty] | 2027-01-04 | [6 empty] | 2027-01-11 | [6 empty] | 2027-01-18 | [6 empty] | 2027-01-25 | [6 empty] | 2027-02-01 | [6 empty] | 2027-02-08 | [6 empty] | 2027-02-15 | [6 empty] | 2027-02-22 | [6 empty] | 2027-03-01 | [6 empty] | 2027-03-08 | [6 empty] | 2027-03-15 | [6 empty] | 2027-03-22 | [6 empty] | 2027-03-29 | [6 empty] | 2027-04-05 | [6 empty] | 2027-04-12 | [6 empty] | 2027-04-19 | [6 empty] | 2027-04-26 | [6 empty] | 2027-05-03 | [6 empty] | 2027-05-10 | [6 empty] | 2027-05-17 | [6 empty] | 2027-05-24 | [6 empty] | 2027-05-31 | [6 empty] | 2027-06-07 | [6 empty] | 2027-06-14 | [6 empty] | 2027-06-21 | [6 empty] | 2027-06-28 | [6 empty] | 2027-07-05 | [6 empty] | 2027-07-12 | [6 empty] | 2027-07-19 | [6 empty] | 2027-07-26 | [6 empty] | 2027-08-02 | [6 empty] | 2027-08-09 | [6 empty] | 2027-08-16 | [6 empty] | 2027-08-23 | [6 empty] | 2027-08-30 | [6 empty] | 2027-09-06 | [6 empty] | 2027-09-13 | [6 empty] | 2027-09-20 | [6 empty] | 2027-09-27 | [6 empty] | 2027-10-04 | [6 empty] | 2027-10-11 | [6 empty] | 2027-10-18 | [6 empty] | 2027-10-25 | [6 empty] | 2027-11-01 | [6 empty] | 2027-11-08 | [6 empty] | 2027-11-15 | [6 empty] | 2027-11-22 | [6 empty] | 2027-11-29 | [6 empty] | 2027-12-06 | [6 empty] | 2027-12-13 | [6 empty] | 2027-12-20
 | time axis 2025-01-20 to 2027-12-26
ID | TASK | START | END | time axis 2025-01-20 to 2027-12-26
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
0 | Phase 0: Project Initiation (4 months)
0-001 | NHSH proposal reviewed and approved by Scottish Government | 2024-12-02 | 2025-01-21
0-002 | Closure of VIG | 2025-01-21 | 2025-02-14
0-003 | Milestone plan drafted | 2025-02-26 | 2025-03-03
0-004 | Project implementation group established with key leads from the HHSCP vaccination teams, GP practices, public health and eHealth | 2025-03-03 | 2025-03-14
0-005 | Define project scope, goals, timeline | 2025-03-03 | 2025-03-17
0-006 | Define the project's governance structure (EDG, LMC, STAG, etc.) | 2025-03-03 | 2025-03-17
0-007 | Stakeholder communications and engagement plan, ensuring clear communications with staff on planning, scope, objectives, benefits | 2025-03-06 | 2025-04-03
0-010 | Develop birth, pre-school and adult service specificiations for vaccination delivery in line with best practice guidelines, including a costing methodology. Service specification also requires to contain clearly defined roles and responsibilities of general practice and HHSCP vaccination staff. Service specification requires detail on GP v. HHSCP immunisation team delivery of specific vaccines. Service specification will outline IT requirements. Local enhanced service specification for adult vaccinations aligned to payment mechanisms outlined in PCA2022-M-07 | 2025-03-06 | 2025-04-03
0-011 | Local strategic vision, aligned with strategic vision produced nationally, approved by Steering Group | 2025-03-13 | 2025-04-03
0-012 | Service specifications to LMC for approval | 2025-05-01 | 2025-05-15
0-013 | Determine framework for eHealth / digital infrastructure to support childhood (birth and pre-school) and adult vaccinations in line with service requirements. Will be required as part of service specifications. | 2025-03-13 | 2025-04-03
0-016 | SLWG formed to develop approach to childhood schedule change | 2025-04-17 | 2025-05-01
0-017 | Approach to childhood schedule change reviewed by implementation group | 2025-05-01 | 2025-05-01
0-018 | Approach to childhood schedule change approved by vaccination governance structure | 2025-05-01 | 2025-05-15
1 | Phase 1: Planning - Birth, Pre-School and Adult Vaccinations in a Collaborative Model (3 months)
1-001 | Child (birth and preschool) and adult service specifications to be offered to all HHSCP GP practices (n=62) with a timescale for sign up by offering a GP opt-in and readiness survey for practices to complete | 2025-04-03 | 2025-04-24
1-002 | Pre-audit for birth, pre-school and adult vaccination service delivery feasibility and assurance criteria is met for delivering service. | 2025-04-24 | 2025-05-29
1-003 | Analyse GP readiness via the pre-audit in line with service specifications and determine the resources needed, including staffing, technology, training and procurement infrastructure | 2025-05-22 | 2025-05-29
1-004 | Review of staffing requirements for HHSCP vaccination teams to support delivery of birth, pre-school and adult vaccinations | 2025-05-29 | 2025-06-05
1-005 | Using results of pre-audit, develop a comprehensive implementation plan with clear timelines for the full rollout, including go-live dates, using a structured three-phase approach across practices and vaccination teams. This plan will define collaborative working arrangements to ensure the effective delivery of both birth and pre-school and adult vaccinations. Adult collaborative vaccination implementation requires to consider the total cohort number of patients eligible. | 2025-05-29 | 2025-06-12
1-006 | Create a training and support plan and associated materials to help GP practices and vaccination teams transition to the new service model, covering clinical protocols, data entry and patient management | 2025-05-29 | 2025-06-12
1-007 | Implement necessary eHealth systems for birth and pre-school vaccination scheduling, reporting and patient tracking across GP practices | 2025-05-15 | 2025-06-26
1-008 | Ensure data-sharing systems compliant with regulations - Conduct DPIA and ensure any risks to data security and patient information are mitigated | 2025-05-15 | 2025-06-12
1-009 | Develop process to continuously and consistently obtain patient feedback from vaccination teams and GPs (i.e. CareOpinion) in new model | 2025-05-15 | 2025-05-29
1-010 | Governance model confirmed across HHSCP vaccination teams and GPs to ensure compliance with national vaccination protocols and best practice guidelines | 2025-05-15 | 2025-05-29
1-011 | Articulate and Establish clear quality assurance framework for monitoring vaccination delivery, including patient safety, data accuracy/quality and adverse event reporting | 2025-05-15 | 2025-05-29
1-012 | Confirm support arrangements to facilitate any issues that may arise during full rollout | 2025-05-29 | 2025-05-29
1-013 | Ensure each GP has detailed guides and SOPs outlining step-by-step procedures for service delivery, PGDs, administration, and data entry | 2025-05-29 | 2025-05-29
1-014 | Establish closed-loop feedback system where GPs can quickly report issues, share successes and offer suggestions for improvement during implementation (phase 2) | 2025-05-22 | 2025-05-29
Pre-implementation
1-015 | Launch communications plan regarding rollout communications to all GP practices and key stakeholders, and include specific instructions for appintment booking, patient management and any changes in procedures in line with new model; also points of contact should there be issues requiring resolution. | 2025-05-29 | 2025-06-26
1-016 | Deliver comprehensive training sessions to all participating GP practices and vaccination teams | 2025-06-12 | 2025-06-26
1-017 | Launch and run public information campaign via the NHSH website, social media, posters at GP practices and in NHSH facilities/hospitals to let patients know how they can receive their vaccinations | 2025-06-12 | 2026-01-30
1-018 | Confirm that the supply chain for vaccines is ready to ensure uninterrupted deliveries to all GP practices based on rollout schedule deployed in delivering phase 2. | 2025-06-12 | 2025-06-19
2 | Phase 2: Implementation of a Collaborative Vaccination Service Delivery Model (6 months)
2-001 | Launch initial birth and pre-school vaccination appointments (phase 1) in selected, opt-in GP practices as part of phased approach | 2025-06-19 | 2025-06-26
2-002 | Analyse data and feedback from GP practices to determine any areas for improvement prior to the second launch of birth and pre-school vaccinations in GP practices as part of phased rollout | 2025-06-26 | 2025-07-03
2-003 | Amend systems/process as required | 2025-06-26 | 2025-07-03
2-004 | Compile report based on phase 1 and communicate outcomes and next steps to EDG / CGC | 2025-06-26 | 2025-07-03
2-005 | Launch subsequent birth and pre-school vaccination appointments (phase 2) in additional opt-in GP practices | 2025-07-03 | 2025-07-17
2-006 | Analyse data and feedback from GP practices to determine any areas for improvement prior to the second launch | 2025-07-17 | 2025-07-24
2-007 | Amend systems/process as required | 2025-07-17 | 2025-07-24
2-008 | Launch phase 3 (final phase) birth and pre-school vaccination appointments in remaining opt-in GP practices | 2025-07-24 | 2025-08-28
2-009 | Monitor data and feedback from GP practices to determine any areas for improvement following the third/final launch | 2025-08-28 | 2025-09-04
2-010 | Conduct monthly evaluations to track progress against KPIs for birth and pre-school immunisation delivery | BAU MONTHLY
2-011 | Local discussion required with GP practices regarding capacity that can be offered to sustain an integrated/hybrid approach to service delivery in line with updated patient cohort data | 2025-07-03 | 2025-07-17
2-012 | Confirm staffing requirements for HHSCP vaccination teams to support delivery of adult vaccinations | 2025-07-17 | 2025-07-31
2-013 | Final checks on staffing and any additional requirements needing to be addressed for adult vaccinations referencing pre-audit tool | 2025-07-31 | 2025-08-28
2-014 | Full mobilsation of adult vaccination service in line with winter vaccination programme | 2025-09-01 | 2026-01-30
3 | Phase 3: Evaluation, Continuous Improvement and Stabilisation (6 months) of a Collaborative Birth, Pre-school and Adult Vaccination Service
3-001 | Use available data to identify areas of improvement in service delivery, patient uptake and efficiency and develop a needs assessment to inform of future service delivery for birth and pre-school vaccinations | 2026-02-05 | 2026-06-04
3-002 | Coupled with the needs assessment, conduct a post-rollout workforce survey to identify areas of success and areas for future improvement | 2026-04-02 | 2026-04-30
3-003 | Using the needs assessment and post rollout survey, develop a plan for the ongoing delivery of birth and pre-school vaccinations, ensuring model is sustainable and aligned to national and local strategic principles | 2026-07-01 | 2026-08-01
3-004 | A robust, external evaluaiton programme to be commissioned, with input as agreed by external stakeholders overseeing developments within collaborative model | TBC | TBC
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one

## Sheet1 (hidden)
Complete | Low
In progress and on track | Medium
On hold | High
In progress but overdue | Critical
Not started

## About (hidden)
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualise and track your project. Simply enter your tasks and start and end dates - no formulae required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colours of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortisation.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organise your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.