## In progress (hidden)
Theme / Culture Priority | Recommendation / activity
Governance and Oversight | Improve profile of Whistleblowing champion and for support for speaking up / whistleblowing
NHSH Board, in addition to regular Board meetings, should receive regular briefings where Board members can receive information from those directly providing front line services
We will have timely data and information to inform our decision making and plans for our future
Culture Priority: Leadership and Management Development | An ongoing cultural improvement development programme should be put in place for all clinical leaders and managers, including members of NHSH Board
Carefully designed, comprehensive training programme addressing appropriate behaviour (including what constitutes bullying and harassment and diversity awareness
Instigate programme of training for staff and managers
Need for authentic leadership and honesty (future, engage, deliver)
Programme of action learning, support and coaching for Managers at all levels, including those preparing for recruitment or promotion into management roles
Programme of awareness and training (managing conflict, mediation skills, management training)
We will ensure appropriate development is in place for all those who have a people leadership role
We will give colleagues skills and tools to have good conversations and challenge appropriately
Communications and Engagement | Improve understanding of extent, nature and distribution of bullying in organisation through direct engagement with staff
Simple, clear and consistent messages to NHSH staff as the norm with regular recognition for work done
The culture going forwards should be one based on engaging and empowering, and valuing contribution through effective appraisal and feedback. This can be monitored through the NHS Scotland i-matter engagement process which all Boards are required to use and report on
We will continue to listen to our colleagues past and present to understand their experiences
We will create opportunities for colleagues to engage with senior leadership and to be heard
We will learn from their experiences and use these insights to inform our future
Employee Wellbeing and Support | Consider strategy for safe spaces and other forums to address issues and build relationships
Culture Priority: Metrics and Tools | Ability to measure culture / bullying in organisation (beyond iMatter)
Breakdown of reasons for sickness as part of HR Indicators
Workforce data not presented in a way that provides assurance that the work to embed the NHS Highland values and supportive behaviours is effective
Organisation and Roles | Reassessment of the relationships between clinicians and managers (clearer management structures, better understanding of the needs and motivations of clinicians and managers and a positive approach)
Role of staffside representation and trade unions requires review, including the partnership agreement
The role of the Employee Director should be clarified to ensure effective representation of the staff side, and effective representation at Board level
Culture Priority: People Processes | A change from a grievance to a resolution based approach, adopted through the HR policies
All HR and other policies to be reviewed and simplified (in context of national reviews) and publicised
An HR case management system is adopted so that all HR processes can be monitored and performance managed. Regular reports on the application of HR policies should be provided to the Staff Governance Committee and the Area Partnership Forum.
Deal with disagreements early and promote civility
Improve reporting of bullying and harassment
Once new starts are in place, induction processes should include training on equality and diversity.
Recruitment processes should be thorough in ensuring that the best candidate is selected, avoiding – and being seen to avoid – any bias, and that those selected have personal values that match those of the organisation, Transparency is key. NHS Scotland has developed a values-based recruitment process which should be adopted for all posts.
Review and amend employment procedures as necessary
Serious consideration is given to external independent involvement in Dignity at Work complaints as the default response
Support and develop HR-related strategies to deal with issues effectively
Support managers in dealing confidently and compassionately with cases of bullying and harassment
Systems for accurate and robust recording of allegations of bullying and harassment
There should be a clear procedure relating to decisions to suspend staff with the circumstances being carefully considered. Suspensions should be regularly reviewed and reported to the Board. This would be supported by the HR case management system referred to in recommendation 10.
We will work together to identify and resolve issues quickly and informally, wherever possible
Culture Programme Management | Agree outcomes / implement measures for each component of the action plan
Confirm the routes of accountability and assurance for the Culture programme, ensure progress reports are based on agreed measurement methodologies and are linked to the relevant action plan
Implement regular and effective review of risk at all Culture Group meetings
Programme plan will be updated and refined with detailed milestones (28 Feb 2021)
Regular reviews with appropriate benchmarks to assess progress in implementing the plan
Review of approach to taking minutes for Culture Group and Staff Governance to assure challenge appropriately provided and recorded
Strategy and Planning | An action plan be developed to capture the organisational learning identified through the IRP process, and that progress be monitored through regular reports and metrics, which can be tracked to monitor improvement, and capture the desired change in culture.
Organisation vision and objectives will be finalised and shared
We will share our vision and priorities in a clear and simple way
Where estate is rationalised a full appraisal of the needs of the service should be undertaken before a move into alternative accommodation is made
Culture Priority: Values and Behaviours / Civility Saves Lives | We will create a workplace where dignity and respect can flourish with zero tolerance for bullying
Civility and respect at all levels – to be driven by the top of the organisation
Develop a behavioural standards framework (not complex) to crystallise what good and bad looks like
Incorporate values and behaviours into induction programmes
Invest in civility / behavioural change – reward the right behaviours
Reinforce a positive culture and supporting behaviours
Review organisational values to ensure positive behaviours in terms of respect and well-being are properly represented
That the concept of a ‘just culture’ be explored and any learning from this be incorporated into the cultural improvement development programme. Progress should be evidenced through a visible decrease in referrals to HR processes
Two different value sets; neither of which link to the performance management framework
We will be clear about what colleagues can expect and what we expect from them, whilst at work
We will embed the NHS Scotland Values in everything we do and the decisions we take
We will focus on Kindness and Civility at an individual level, right across our organisation

## Sturrock recommendations
Theme | Sturrock Recommendation | Status: Blue: Complete Green: On track Amber: Delayed Red: Not yet started | Action 1 | Action 2
Capability | Ongoing support training for the leadership team, including regular support and coaching and networking / support from other relevant public sector organisations in Scotland | Completed | Systems Leadership training with Kings Fund underway, completing Summer 2022 and then further rollout planned | Exec Directors fortnightly development session in place since March 2021 includes senior leaders every other session. Board development programme in place.
| Instigate programme of training for staff and managers | Completed | Once for Scotland training delivered in conjunction with staffside | Leadership and Management development programme in place.
| Carefully designed, comprehensive training programme addressing appropriate behaviour (including what constitutes bullying and harassment and diversity awareness) | Green | Courageous Conversations training delivered to over 1000 colleagues since July 2020, with online module launching in March 2022 | NHS Highland has recently agreed to adopt the "Promoting Professionalism" approach of Vanderbilt which will further address this.
| Programme of action learning, support and coaching for Managers at all levels, including those preparing for recruitment or promotion into management roles | Completed | Leadership and Maangement development programme levels 1-4 launched in October 2021 with 72 particpants and further rollout planned
Communications and Engagement | Listening exercise for individuals who did not have the opportunity to participate | Completed | Healing Process designed and launched in May 2020, will conclude in March 2022 | Regular listening and learning visits across the board area by execs and non execs since September 2019
| Simple, clear and consistent messages to NHSH staff as the norm with regular recognition for work done | Completed | Regular Chief Executive V-logs, Ask Me Anything sessions, Weekly update emails | Significant staff and patient engagement completed as part of the recent strategy development process.
| Simple, well thought out and transparent information to the community to help rebuild confidence | Completed | 2 x engagement posts filled to support effectivie engagement internally and externally | Significant staff and patient engagement completed as part of the recent strategy development process.
| Streamlined and realistic communications strategy to direct information more effectively to the target audience | Completed | Communications and Engagement strategy approved in May 2021 and progress updated to Staff Governance committee
| Adopt social media and communication standards so that simple, clear, consistent and regular messages to staff become the norm | Completed | Revisied policy and guidance approved and communicated.
Employee Wellbeing and Support | Greater support for mental health (including from Occupational Health) | Completed | Employee Assistance Programme in place since May 2020 including access to counselling and support | Part time Psycholgist bsaed within OH, as well as 2 x CBT / EMDR therapists
| Creation of independent and confidential support for Speaking up / Whistleblowing that all staff are aware of how to use | Completed | Independent Guardian Speak Up service in place since August 2020
| Consider strategy for safe spaces and other forums to address issues and build relationships | Completed | Promotion of Guardians, EAP, staffside, chaplaincy, peer support and Whistleblowing
| Staff to have the time and facilities to meet and reflect, rest and meet colleagues away from immediate patient-facing pressures | Green | Delayed due to Covid, but a core strand of our 2022 wellbeing strategy and plan is to make additional space available
Governance and Oversight | New style of people-centred leadership with more effective and competent Board | Completed | Leadership focussed on people and working as a system, board (execs and non execs) operating well and providing strong challenge and oversight
| Resetting of Executive team and senior managers | Completed | Investment in new leadership posts and attraction of many high quality leaders including Chief Exec, Chief Officers, Directors of Estates and People and Culture as well as Public Health
| Review of Governance structures, committee network and culture to enable clear communication and decision-making | Completed | Full review and radical transformation of governance approach and effectiveness carried out.
| Review of Board appointments, including training and support for NEDs | Completed | Ongoing programme of board develoopment, structured induction and support, with around 70% of the NEDs new in post in the last 3 years.
| Board to exercise governance function well; review governance structures | Completed | Full review carried out, significant changes made. Internal audiit review of board assurance conducted and actions are being implemented
| Non-Executive Board members to be trained and supported | Completed | As above, full induction and development programme in place.
| Review management and other arrangements in Argyll and Bute | Green | New Chief Officer appointed in Feb 2022, significant changes to leadership roles and ongoing review of SLT structure and governance.
| Separate review of the functioning / management of Argyll and Bute | Completed | Culture Survey completed in May 2020, findings broadly similar to Sturrock with some specific issues which have been actioned locally
Healing | Support for individuals who have experienced harm or distress | Completed | Psychological Therapies being provided as part of Healing Process, with £0.5m treatment and support approved | Support for colleagues also in place via EAP, OH and other channels.
Organisation and Roles | Reassessment of the relationships between clinicians and managers (clearer management structures, better understanding of the needs and motivations of clinicians and managers and a positive approach) | Green | New Chair of Area Clinical Forum in place, Chief Exec and others have invested significant time in engaging with clinicians and ensuring they are heard and engaged, this is continuing with the strategy development process.
| System for addressing complaints or differences of professional view needed (and use of facilitation / mediation) | Green | Multiple channels for colleague concerns to be raised in place and being well used, including WB standard and Guardian Service | A wider review of our approach to patient experience, feedback and complaints is part of our strategic plan and will be addressed there.
| Role of staffside representation and trade unions requires review, including the partnership agreement | Completed | A new Employee Director is in place, strong partnership working is in place with staffside attending all relevant meetings including senior leadership and improved understanding of engagement.
| Relationship of GP practices to NHSH needs review (to forge mutual understanding and respect) | Green | Chief Executive and senior colleagues investing signicant time and effort into this, with some postiive results and a survey was recently carried out. | Further work on this will be achieved via our strategy and ambitions.
People Processes & Policies | Review use of suspension (utilised only in exceptional circumstances) | Completed | Suspensions now rare and short term, approved by Directors only.
| Deal with disagreements early and promote civility | Green | Early resolution embedded and used in 30 of 35 cases in 2021/2. | Civility Saves Lives / Promoting Professionalism rollout delayed due to systems pressures but a key focus for 2022/3 and part of our strategy going forwards
| Support and develop HR-related strategies to deal with issues effectively | Completed | Investment in OD support for teams and individuals, a range of tools used to support challenging situations. Early resolution strongly promoted by HR and Staffside | Dedicated OD team in place
| All HR and other policies to be reviewed and simplified (in context of national reviews) and publicised | Completed | Once for Scotland policies rolled out, internal review of people processes and increased training in place
| Systems for accurate and robust recording of allegations of bullying and harassment | Green | Local reporting is now in place and being reviewed at all levels. | System is paused whilst national systems strategy is defined.
| Organisation wide clarity on the role of HR | Green | Investment in new posts, People Partners in place to support operational leadership in a strategic role and new structure in place | Further engagement work on this is being rolled out in 2022/3 as part of our strategy.
Strategy and Planning | Implement a collaborative, participative approach to developing strategy and defining the way ahead | Completed | Together we care, our 5 year strategy for 2022 and beyond is being co-created in our most extensive engagement and particpation exercise ever, due to be confirmed in July 2022
| Forward looking strategic plan and a shared vision | Completed | One year plan for 2021/2 was put in place and being delivered against, with vision, values and board objectives, and the Together we Care strategy will come into being in July 2022
Values and Behaviours | Civility and respect at all levels – to be driven by the top of the organisation | Green | Executives, Non Executives and Senior Managers have been role modelling the values and behaviours and acting with dignity and respect. | Our Team conversations initaitve is being rolled out in 2022 to support this at a local level